## Dashboard
Dated: | [6 empty] | Daily Activity Report
2021-09-20
PM: Khalid Najmi
Region | Allocated Teams | Total Allocated Activities | Clock-in Status |  |  | EHS Status |  | Activity Status |  |  |  |  | ATP Status
|  |  | On-Time | Late | No Show | Closed | Rejected/Closed | Completed | In progress | Pending | Closed | Rejected | Done
North | 9 | 10 | 5 | 3 | 2 | 7 | 1 | 4 | 3 | 3 |  |  | 0
Center | 6 | 7 | 2 | 2 | 3 | 3 | 1 | 3 | 2 | 2 |  |  | 2
Total | 15 | 17 | 7 | 5 | 5 | 10 | 2 | 7 | 5 | 5 |  |  | 2
Grand Total | 15 | 17 | 17 |  |  | 12 |  | 17 |  |  |  |  | 2
Total Idle Teams: |  |  |  | 01 team is on leave in Noth , 01 team in center could not move as T/L gor faimly urgency.
Nos of activities with SLA breach: |  |  |  | 05 activities breached the XAD internal SLA
Date | Region | DU ID |  |  |  |  | Activity | T/L |  | Total Planned days | SLA Breach aging
2021-09-09 | North | RWP5171_2G-L900-LTE_NEW_P |  |  |  |  | ATP | xad_Atif |  | 6 | 3
2021-09-09 | North | 51212-GL900-Exp-P |  |  |  |  | Survey | xad_Atif |  | 4 | 3
2021-09-09 | North | 51747-GL900-Exp-P |  |  |  |  | Survey | xad_Atif |  | 3 | 2
2021-09-09 | North | 3165-POWER-EXP-K |  |  |  |  | Survey | xad_shahzad1 |  | 3 | 2
2021-09-09 | North | 51141-8338_MW_EXP_NEW_K |  |  |  |  | ATP | xad_waseem |  | 5 | 2

## Daily plan (hidden)
Xad Technologies LTD.
| Huawei |  |  |  | HUAWEI Core |  | REON |  | NOKIA |  |  | NAYATEL |  | Grand
Projects | H.Centre | H.North | H.South | H. Total | H.Centre | H.Total | REON | N.Total | N.MW Central | N.MW North | N.Total | NAYATEL | N.Total | Total | Info Dashboard
Implementations Manager | Khalid Najmi | Khalid Najmi | Khalid Najmi |  | Ali Jaffri |  | M.Zeeshan |  | Khalid Najmi | Khalid Najmi |  | AlI Jaffri
2021-09-21 | [14 empty] | Huawei Central : 2 Teams are awaiting for work of scope
Teams | 5 | 9 | 0 | 14 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 20
Huawei South : 1 Team is awaiting for work of scope
RPM | 1 | 1 |  | 2 |  | 0 |  | 0 |  |  | 0 |  | 0 | 2
DRPM | 1 | 1 | 1 | 3 |  | 0 |  | 0 |  |  | 0 |  | 0 | 3 | HUAWEI North : Team is waiting for SMR
Engineer | 6 | 6 | 2 | 14 |  | 0 |  | 0 |  |  | 0 |  | 0 | 14
Technician | 3 | 2 | 1 | 6 |  | 0 |  | 0 |  |  | 0 |  | 0 | 6 | NOKIA North : Team is waiting for Funds against rectification activity
Riggers | 15 | 15 | 2 | 32 |  | 0 |  | 0 |  |  | 0 |  | 0 | 32
Trainee _ Rigger |  |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 | 0 | REON : Team is waiting for Funds against rectification activity
Helper |  |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 | 0
Total | 26 | 25 | 6 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57
Vehicles.
Carry Bolan | 6 | 6 | 1 | 13 |  | 0 |  | 0 |  |  | 0 |  | 0 | 13
Vehicles 4x4 |  |  |  | 0 | [9 empty] | 0
HIACE |  |  |  | 0 | [9 empty] | 0
Total | 6 | 6 | 1 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13

## Sheet5 (hidden)
Region | (All)
Row Labels | Count of DU ID | Count of Clock in Status | Count of EHS Status | Count of Q/C Status | Count of ATP Status
August | 74 | 64 | 48 | 40
2021-08-25 | 15 | 15 | 10 | 15
2021-08-26 | 9 | 9 | 6 | 9
2021-08-27 | 10 | 10 | 7 | 10
2021-08-28 | 10
2021-08-29 | 10 | 10 | 9
2021-08-30 | 10 | 10 | 7
2021-08-31 | 10 | 10 | 9 | 6
Grand Total | 74 | 64 | 48 | 40

## North
[5 empty] | 199 |  | 199 |  | 2021-09-21 |  | 56
Date | Quarter | Year | Month | Region | DU ID | Activity | Team Lead | Total Planned days | SLA Breach aging | Team Status | Clock in Status | EHS Status | Activity Status | Q/C Status | ATP Status | Remarks
2021-08-25 | 3 | 2021 | August | North | KHB2294_LTE_NEW_F | Wireless I&C | xad_ghazenfar | 1 |  | Utilized | On Time | Closed | In progress | In review
2021-08-25 | 3 | 2021 | August | North | RWP5171_2G-L900-LTE_NEW_P | MW I&C | xad_adeel | 1 |  | Utilized | Late | Closed | In progress | In review
2021-08-25 | 3 | 2021 | August | North | RWP5171_RWP1213_Link_1_P | MW I&C | xad_adeel | 1 |  | Utilized | No Show |  | Pending | In review
2021-08-25 | 3 | 2021 | August | North | RUR0424_BIL1742_Link_1_A | MW I&C | xad_Hasnain | 1 |  | Utilized | Late | Closed | In progress | Rejected
2021-08-25 | 3 | 2021 | August | North | 52205-POWER-EXP-I | Power I&C | xad_akbar1 | 1 |  | Utilized | On Time | Closed | Completed | Closed
2021-08-25 | 3 | 2021 | August | North | 52099-POWER-EXP-I | Power I&C | xad_adnan | 1 |  | Utilized | No Show |  | Completed | In review
2021-08-25 | 3 | 2021 | August | North | UFMGY3 Opex_N-4809_PWR_Swap_K | Power I&C | xad_adnan | 1 |  | Utilized | No Show |  | Pending | Not applicable
2021-08-25 | 3 | 2021 | August | North | 8425-GL900-Exp-A | Wireless I&C | xad_Saqib | 1 |  | Utilized | On Time | Closed | Completed | Closed
2021-08-25 | 3 | 2021 | August | North | 51425-POWER-NOMC-K | Power Survey | xad_atif | 1 |  | Utilized | On Time | Closed | Completed | Not applicable
2021-08-25 | 3 | 2021 | August | North | 8109-POWER-NOMC-K | Power Survey | xad_atif | 1 |  | Utilized | On Time | Closed | Pending | Not applicable
2021-08-25 | 3 | 2021 | August | North | 51255-POWER-EXP-P | Power Survey | xad_Shahzad1 | 1 |  | Utilized | Late | Closed | Completed | Not applicable
2021-08-25 | 3 | 2021 | August | North | 51256-POWER-EXP-P | Power Survey | xad_Shahzad1 | 1 |  | Utilized | Late | Closed | Pending | Not applicable
2021-08-25 | 3 | 2021 | August | North | 51963-POWER-EXP-P | Power Survey | Xad_zain | 1 |  | Utilized | No Show |  | Pending | Not applicable
2021-08-25 | 3 | 2021 | August | North | 51969-POWER-EXP-P | Power Survey | Xad_zain | 1 |  | Utilized | No Show |  | Pending | Not applicable
2021-08-25 | 3 | 2021 | August | North | 52707-8057_MW_OMT_NEW_P | MW I&C | Xad_baseer | 1 |  | Utilized | On Time | Rejected/closed | Completed | Rejected
2021-08-26 | 3 | 2021 | August | North | KHB2294_LTE_NEW_F | Wireless I&C | xad_ghazenfar | 2 |  | Utilized | On Time | Closed | Completed | In review
2021-08-26 | 3 | 2021 | August | North | 52719-GL900-Exp-I | Wireless I&C | xad_adeel | 1 |  | Utilized | Late | Closed | In progress | In review
2021-08-26 | 3 | 2021 | August | North | RUR0424_BIL1742_Link_1_A | MW I&C | xad_Hasnain | 2 |  | Utilized | Late | Rejected/Closed | Completed | Rejected
2021-08-26 | 3 | 2021 | August | North | UFMGY3 Opex_8884_PWR_Swap_K | Power I&C | xad_adnan | 1 |  | Utilized | On Time | Closed | Completed | Rejected
2021-08-26 | 3 | 2021 | August | North | 52099-POWER-EXP-I | Power I&C | xad_akbar1 | 2 |  | Utilized | On Time | Closed | Completed | Rejected
2021-08-26 | 3 | 2021 | August | North | 9352-POWER-NOMC-A | QC Completion | xad_Saqib | 1 |  | Utilized | No show |  | Pending | In review
2021-08-26 | 3 | 2021 | August | North | 51418-POWER-EXP-P | Survey | xad_atif | 1 |  | Utilized | No show |  | Pending | Not applicable
2021-08-26 | 3 | 2021 | August | North | 51963-POWER-EXP-P | Survey | xad_waseem | 2 | 1 | Utilized | No show |  | Pending | Not applicable
2021-08-26 | 3 | 2021 | August | North | 3320-9710_MW_SWAP_NEW_P | MW I&C | Xad_baseer | 1 |  | Utilized | Late | Rejected/Closed | In progress | In review
2021-08-27 | 3 | 2021 | August | North | 53197-9192_MW_NPS_NEW_P | MW I&C | Xad_saqib | 1 |  | Utilized | Late | Closed | In progress | Not Attempted
2021-08-27 | 3 | 2021 | August | North | 9352-POWER-NOMC-A | QC Completion | Xad_hasnain | 2 |  | Utilized | No show |  | Pending | Not Attempted
2021-08-27 | 3 | 2021 | August | North | 8329-9398_MW_OMT_NEW_P | MW I&C | Xad_Shahzad1 | 1 |  | Utilized | Late | Closed | In progress | In review
2021-08-27 | 3 | 2021 | August | North | 51418-POWER-EXP-P | Survey | Xad_atif | 2 | 1 | Utilized | Late |  | Completed | Not applicable
2021-08-27 | 3 | 2021 | August | North | 51963-POWER-EXP-P | Survey | Xad_waseem | 3 | 2 | Utilized | No show |  | Pending | Not applicable
2021-08-27 | 3 | 2021 | August | North | 52719-GL900-Exp-I | Wireless I&C | Xad_adeel | 2 |  | Utilized | Late | Closed | Completed | In review
2021-08-27 | 3 | 2021 | August | North | 3320-9710_MW_SWAP_NEW_P | MW I&C | Xad_baseer | 2 |  | Utilized | On Time | Closed | Completed | In review
2021-08-27 | 3 | 2021 | August | North | KHB2295_LTE_NEW_F | Wireless I&C | Xad_ghazenfar | 1 |  | Utilized | On Time | Closed | In progress | Not Attempted
2021-08-27 | 3 | 2021 | August | North | ISB4372_L2100_NEW_I | Wireless I&C | Xad_akbar1 | 1 |  | Utilized | Late | Closed | In progress | Not Attempted
2021-08-27 | 3 | 2021 | August | North | UFMGY3 Opex_6635_PWR_Swap_K | Power I&C | Xad_adnan | 1 |  | Utilized | On Time | Closed | Pending | Not Attempted
2021-08-28 | 3 | 2021 | August | North | 53197-POWER-NEW-P | Power I&C | Xad_saqib | 1 |  | Utilized |  |  | In progress | Closed
2021-08-28 | 3 | 2021 | August | North | 8329-9398_MW_OMT_NEW_P | MW I&C | Xad_Shahzad1 | 2 |  | Utilized |  |  | Completed
2021-08-28 | 3 | 2021 | August | North | 51418-POWER-EXP-P | Survey | Xad_atif | 3 | 2 | Utilized |  |  | Completed
2021-08-28 | 3 | 2021 | August | North | 51963-POWER-EXP-P | Survey | Xad_waseem | 4 | 3 | Utilized |  |  | Completed
2021-08-28 | 3 | 2021 | August | North | 50795-GL900-Exp-P | Wireless I&C | Xad_adeel | 1 |  | Utilized |  |  | In progress
2021-08-28 | 3 | 2021 | August | North | 52711-3G-4G-NEW-P | QC Completion | Xad_baseer | 1 |  | Utilized |  |  | In progress
2021-08-28 | 3 | 2021 | August | North | NTH5200_2G-4G_NEW_P | QC Completion | Xad_hasnain | 1 |  | Utilized |  |  | Pending
2021-08-28 | 3 | 2021 | August | North | KHB2295_LTE_NEW_F | Wireless I&C | Xad_ghazenfar | 2 |  | Utilized |  |  | Completed | Closed
2021-08-28 | 3 | 2021 | August | North | ISB4372_L2100_NEW_I | Wireless I&C | Xad_akbar1 | 2 |  | Utilized |  |  | In progress
2021-08-28 | 3 | 2021 | August | North | UFMGY3 Opex_6635_PWR_Swap_K | Power I&C | Xad_adnan | 2 |  | Utilized |  |  | Completed
2021-08-29 | 3 | 2021 | August | North | 53197-3G-4G-NEW-P | Wireless I&C | Xad_saqib | 1 |  | Utilized | On Time | Closed | In progress
2021-08-29 | 3 | 2021 | August | North | 51106-POWER-EXP-I | Power I&C | Xad_Shahzad1 | 1 |  | Utilized | Late | Closed | In progress
2021-08-29 | 3 | 2021 | August | North | 51604-POWER-EXP-P | Survey | Xad_atif | 1 |  | Utilized | Late | Closed | Completed
2021-08-29 | 3 | 2021 | August | North | 50795-GL900-Exp-P | Wireless I&C | Xad_adeel | 2 |  | Utilized | Late | Closed | Completed
2021-08-29 | 3 | 2021 | August | North | 52711-3G-4G-NEW-P | QC Completion | Xad_baseer | 2 |  | Utilized | On Time | Closed | Completed
2021-08-29 | 3 | 2021 | August | North | RWP5171_RWP1213_Link_1_P | QC Completion | Xad_wasim | 2 |  | Utilized | Late | Closed | Pending
2021-08-29 | 3 | 2021 | August | North | NTH5200_2G-4G_NEW_P | QC Completion | Xad_hasnain | 2 |  | Utilized | No Show |  | Pending
2021-08-29 | 3 | 2021 | August | North | KHB7148_LTE_NEW_F | Wireless I&C | Xad_ghazenfar | 1 |  | Utilized | On Time | Closed | In progress
2021-08-29 | 3 | 2021 | August | North | ISB4364_L2100_NEW_I | Wireless I&C | Xad_akbar1 | 1 |  | Utilized | Late | Closed | In progress
2021-08-29 | 3 | 2021 | August | North | BIL0954_RRU-MOD_NEW_P | Power I&C | Xad_adnan | 1 |  | Utilized | Late | Closed | In progress
2021-08-30 | 3 | 2021 | August | North | 53197-3G-4G-NEW-P | Wireless I&C | Xad_saqib | 2 |  | Utilized | On Time | Closed | Completed | Closed
2021-08-30 | 3 | 2021 | August | North | 51969-POWER-EXP-P | Survey | Xad_atif | 2 | 1 | Utilized | On Time | closed | Completed
2021-08-30 | 3 | 2021 | August | North | 9513-8027_MW_OMT_NEW_K | Power I&C | Xad_Shahzad1 | 1 |  | Utilized | No Show |  | In progress
2021-08-30 | 3 | 2021 | August | North | 53000-GL900-EXP-A | Wireless I&C | Xad_adeel | 1 |  | Utilized | No Show |  | In progress
2021-08-30 | 3 | 2021 | August | North | 3066-POWER-NOMC-P | Power I&C | Xad_baseer | 1 |  | Utilized | Late | closed | In progress
2021-08-30 | 3 | 2021 | August | North | NTH5200_2G-4G_NEW_P | QC Completion | Xad_hasnain | 3 |  | Utilized | No Show |  | Pending
2021-08-30 | 3 | 2021 | August | North | KHB7148_LTE_NEW_F | Wireless I&C | Xad_ghazenfar | 2 |  | Utilized | On Time | Closed | In progress
2021-08-30 | 3 | 2021 | August | North | ISB4364_L2100_NEW_I | Wireless I&C | Xad_akbar1 | 2 |  | Utilized | On Time | closed | In progress
2021-08-30 | 3 | 2021 | August | North | BIL0954_RRU_MOD_NEW_P | Wireless I&C | Xad_adnan | 1 |  | Utilized | On Time | closed | In progress
2021-08-30 | 3 | 2021 | August | North | UFMGY3 Opex_2687_PWR_Swap_K | Power I&C | Xad_Imran | 1 |  | Utilized | Late | closed | In progress
2021-08-31 | 3 | 2021 | August | North | 3160-POWER-NOMC-P | Power I&C | Xad_saqib | 1 |  | Utilized | On Time | Closed | In progress | Closed
2021-08-31 | 3 | 2021 | August | North | 51256-POWER-EXP-P | Survey | Xad_atif | 2 | 1 | Utilized | On Time | Closed | Completed | Not applicable
2021-08-31 | 3 | 2021 | August | North | 9513-8027_MW_OMT_NEW_K | Power I&C | Xad_Shahzad1 | 2 |  | Utilized | No Show |  | Pending
2021-08-31 | 3 | 2021 | August | North | 53000-GL900-EXP-A | Wireless I&C | Xad_adeel | 2 |  | Utilized | Late | Closed | In progress
2021-08-31 | 3 | 2021 | August | North | 3066-POWER-NOMC-P | Power I&C | Xad_baseer | 2 |  | Utilized | On Time | Rejected/closed | In progress
2021-08-31 | 3 | 2021 | August | North | 9349-POWER-NOMC-A | Power I&C | Xad_Imran | 1 |  | Utilized | Late | Closed | In progress | Rejected
2021-08-31 | 3 | 2021 | August | North | NTH5200_2G-4G_NEW_P | QC Completion | Xad_hasnain | 4 | 1 | Utilized | On Time | Closed | Pending | Closed
2021-08-31 | 3 | 2021 | August | North | KHB7148_LTE_NEW_F | Wireless I&C | Xad_ghazenfar | 3 |  | Utilized | On Time | Closed | In progress
2021-08-31 | 3 | 2021 | August | North | ISB4364_L2100_NEW_I | Wireless I&C | Xad_akbar1 | 3 |  | Utilized | On Time | Closed | In progress | Rejected
2021-08-31 | 3 | 2021 | August | North | BIL0954_RRU-MOD_NEW_P | Wireless I&C | Xad_adnan | 2 |  | Utilized | Late | Closed | Completed | Closed
2021-09-01 | 3 | 2021 | September | North | 52151-POWER-NEW-P | Power I&C | xad_saqib | 1 |  | Utilized | On Time | Closed | Completed
2021-09-01 | 3 | 2021 | September | North | 53000-GL900-EXP-A | QC Completion | xad_adeel | 3 |  | Utilized | On Time | Closed | Completed | Closed
2021-09-01 | 3 | 2021 | September | North | 51141-8338_MW_EXP_NEW_K | Rectification | xad_imran | 1 |  | Utilized | No Show |  | Pending
2021-09-01 | 3 | 2021 | September | North | 9667-POWER-EXP-P | Survey | xad_atif | 1 |  | Utilized | Late | Closed | Completed
2021-09-01 | 3 | 2021 | September | North | 9349-POWER-NOMC-A | Power I&C | xad_shahzad1 | 2 |  | Utilized | No Show |  | Completed | Closed
2021-09-01 | 3 | 2021 | September | North | 52711-3G-4G-NEW-P | ATP | xad_baseer | 3 |  | Utilized | Late | Closed | Completed | Closed | Done
2021-09-01 | 3 | 2021 | September | North | KTA2615_RRU-MOD_NEW_P | Rectification | xad_hasnian | 1 |  | Utilized | Late | Closed | Completed
2021-09-01 | 3 | 2021 | September | North | RWP5171_2G-L900-LTE_NEW_P | QC Closure | xad_wasim | 2 |  | Utilized | No Show |  | Pending
2021-09-01 | 3 | 2021 | September | North | ISB4372_L2100_NEW_I | QC Closure | xad_akbar1 | 3 |  | Utilized | late | Closed | In progress | Closed
2021-09-02 | 3 | 2021 | September | North | 53001-GL900-EXP-A | Wireless I&C | xad_saqib | 1 |  | Utilized | No Show |  | In progress
2021-09-02 | 3 | 2021 | September | North | 50795-GL900-Exp-P | QC Completion | xad_adeel | 3 |  | Utilized | Late | Closed | Completed | Closed
2021-09-02 | 3 | 2021 | September | North | 51141-8338_MW_EXP_NEW_K | Rectification | xad_hasnian | 2 |  | Utilized | Late | Closed | In progress
2021-09-02 | 3 | 2021 | September | North | 52188-GL900-EXP-P | Survey | xad_atif | 1 |  | Utilized | Late | Closed | Pending
2021-09-02 | 3 | 2021 | September | North | 51960-POWER-EXP-P | Survey | xad_shahzad1 | 1 |  | Utilized | Late | Closed | Completed
2021-09-02 | 3 | 2021 | September | North | 53197-3G-4G-NEW-P | ATP | xad_baseer | 3 |  | Utilized | Late | Closed | Completed |  | Done
2021-09-02 | 3 | 2021 | September | North | BIL0954_RRU_MOD_NEW_P | ATP | xad_wasim | 2 |  | Utilized | No Show |  | Completed |  | Done
2021-09-02 | 3 | 2021 | September | North | RWP5171_2G-L900-LTE_NEW_P | QC Closure | xad_akbar1 | 3 |  | Utilized | On Time | Closed | Pending
2021-09-02 | 3 | 2021 | September | North | KHB7148_LTE_NEW_F | Wireless I&C | xad_ghazenfar | 4 | 1 | Utilized | On Time | Closed | Pending | Closed
2021-09-03 | 3 | 2021 | September | North | 53001-GL900-EXP-A | Wireless I&C | xad_saqib | 2 |  | Utilized | On Time | Closed | In progress
2021-09-03 | 3 | 2021 | September | North | 52188-GL900-EXP-P | Survey | xad_atif | 2 | 1 | Utilized | On Time | Closed | Pending
2021-09-03 | 3 | 2021 | September | North | 3165-POWER-EXP-K | Survey | xad_shahzad1 | 1 |  | Utilized | late | Closed | In progress
2021-09-03 | 3 | 2021 | September | North | 51205-POWER-EXP-P | Survey | xad_waseem | 1 |  | Utilized | No Show |  | Pending
2021-09-03 | 3 | 2021 | September | North | 9352-POWER-NOMC-A | ATP | xad_akbar1 | 3 |  | Utilized | No Show |  | Pending
2021-09-03 | 3 | 2021 | September | North | 51545-POWER-NOMC-P | ATP | xad_baseer | 1 |  | Utilized | No Show |  | Completed |  | Done
2021-09-03 | 3 | 2021 | September | North | 50284-POWER-NOMC-P | ATP | xad_ghazenfar | 1 |  | Utilized | No Show |  | Pending
2021-09-03 | 3 | 2021 | September | North | 52099-POWER-EXP-I | ATP | xad_hasnian | 3 |  | Utilized | No Show |  | Pending
2021-09-03 | 3 | 2021 | September | North | ISB4364_L2100_NEW_I | ATP | xad_imran | 4 | 1 | Utilized | No Show |  | Completed | Closed | Done
2021-09-03 | 3 | 2021 | September | North | RWP5171_2G-L900-LTE_NEW_P | QC Closure | xad_adeel | 4 | 1 | Utilized | late | Closed | Completed | Closed
2021-09-04 | 3 | 2021 | September | North | 53001-GL900-EXP-A | Wireless I&C | xad_saqib | 3
2021-09-04 | 3 | 2021 | September | North | 52056-GL900-EXP-P | Survey | xad_atif | 1
2021-09-04 | 3 | 2021 | September | North | 3165-POWER-EXP-K | Survey | xad_shahzad1 | 2 | 1
2021-09-04 | 3 | 2021 | September | North | 8329-9398_MW_OMT_NEW_P | ATP | xad_baseer | 3
2021-09-04 | 3 | 2021 | September | North | 9344-POWER-NOMC-A | ATP | xad_akbar1 | 1
2021-09-04 | 3 | 2021 | September | North | 50758-POWER-EXP-P | ATP | xad_ghazenfar | 1
2021-09-04 | 3 | 2021 | September | North | 52707-8057_MW_OMT_NEW_P | ATP | xad_waseem | 2
2021-09-04 | 3 | 2021 | September | North | 3320-9710_MW_SWAP_NEW_P | ATP | xad_imran | 3
2021-09-04 | 3 | 2021 | September | North | BIL0954_RRU_MOD_NEW_P | ATP | xad_hasnian | 3
2021-09-04 | 3 | 2021 | September | North | 51212-GL900-EXP-P | Survey | xad_atif | 1
2021-09-04 | 3 | 2021 | September | North | 51747-GL900-EXP-P | Survey | xad_imran | 1
2021-09-04 | 3 | 2021 | September | North | 50795-GL900-Exp-P | QC Completion | xad_akbar1 | 4 | 1
2021-09-05 | 3 | 2021 | September | North | 50795-GL900-Exp-P | Troubleshooting | xad_saqib | 5 | 2 |  |  |  |  | Closed
2021-09-05 | 3 | 2021 | September | North | 52854-GL900-Exp-P | Survey | xad_atif | 1
2021-09-05 | 3 | 2021 | September | North | 51215-GL900-Exp-P | Survey | xad_imran | 1
2021-09-05 | 3 | 2021 | September | North | 52003-POWER-EXP-I | Survey | xad_shahzad1 | 1
2021-09-05 | 3 | 2021 | September | North | 52099-POWER-EXP-I | Troubleshooting | xad_akbar1 | 4 | 1 |  |  |  |  | Closed
2021-09-05 | 3 | 2021 | September | North | 3066-POWER-NOMC-P | QC Closure | xad_hasnian | 3
2021-09-05 | 3 | 2021 | September | North | 51212-GL900-EXP-P | Survey | xad_atif | 2 | 1
2021-09-05 | 3 | 2021 | September | North | 51747-GL900-EXP-P | Survey | xad_imran | 2 | 1
2021-09-06 | 3 | 2021 | September | North | 52099-POWER-EXP-I | ATP | xad_akbar1 | 5 | 2 | Utilized | No Show |  | Completed |  | Done
2021-09-06 | 3 | 2021 | September | North | 9352-POWER-NOMC-A | ATP | xad_waseem | 4 | 1 | Utilized | No Show |  | Pending
2021-09-06 | 3 | 2021 | September | North | BIL0954_RRU_MOD_NEW_P | ATP | xad_hasnian | 4 | 1 | Utilized | No Show |  | Completed |  | Done
2021-09-06 | 3 | 2021 | September | North | 3346-POWER-EXP-I | Power I&C | xad_saqib | 1 |  | Utilized | Late | Closed | Pending
2021-09-06 | 3 | 2021 | September | North | 9751-9495_MW_OMT_NEW_K | MW I&C | xad_baseer | 1 |  | Utilized | Late | Rejected/Closed | In progress | Closed
2021-09-06 | 3 | 2021 | September | North | 51745-GL900-Exp-P | Survey | xad_atif | 1 |  | Utilized | Late | Closed | Pending
2021-09-06 | 3 | 2021 | September | North | 50831-POWER-EXP-I | Survey | xad_shahzad1 | 1 |  | Utilized | Late | Closed | Completed
2021-09-06 | 3 | 2021 | September | North | 9989-GL900-Exp-P | Survey | xad_ghazenfar | 1 |  | Utilized | Late | Closed | Pending
2021-09-06 | 3 | 2021 | September | North | 51212-GL900-Exp-P | Survey | xad_imran | 3 | 2 | Utilized | Late | Closed | Completed
2021-09-07 | 3 | 2021 | September | North | 51106-POWER-EXP-I | ATP | xad_akbar1 | 2 |  | Utilized | No show |  | Completed |  | Done
2021-09-07 | 3 | 2021 | September | North | 9344-POWER-NOMC-A | ATP | xad_waseem | 2 |  | Utilized | No show |  | Completed |  | Done
2021-09-07 | 3 | 2021 | September | North | 51141-8338_MW_EXP_NEW_K | ATP | xad_hasnian | 3 |  | Utilized | No show |  | Pending
2021-09-07 | 3 | 2021 | September | North | 50831-POWER-EXP-I | Power I&C | xad_saqib | 2 |  | Utilized | On Time | Closed | Pending
2021-09-07 | 3 | 2021 | September | North | 50251-GL900-Exp-P | Survey | xad_baseer | 1 |  | Utilized | No show |  | Pending
2021-09-07 | 3 | 2021 | September | North | 51745-GL900-Exp-P | Survey | xad_atif | 2 | 1 | Utilized | On Time | Closed | Completed
2021-09-07 | 3 | 2021 | September | North | 50024-POWER-EXP-P | Survey | xad_shahzad1 | 1 |  | Utilized | On Time | Closed | Completed
2021-09-07 | 3 | 2021 | September | North | 9989-GL900-Exp-P | Survey | xad_ghazenfar | 2 | 1 | Utilized | Late | Closed | Pending
2021-09-07 | 3 | 2021 | September | North | 51201-GL900-Exp-P | Survey | xad_imran | 1 |  | Utilized | On Time | Rejected/closed | Pending
2021-09-08 | 3 | 2021 | September | North | 50969-POWER-EXP-I | Power I&C | xad_saqib | 1 |  | Utilized | No Show |  | Pending |  |  | Access issue
2021-09-08 | 3 | 2021 | September | North | RWP5171_2G-L900-LTE_NEW_P | ATP | xad_waseem | 5 | 2 | Utilized | No Show |  | Pending |  |  | Rain
2021-09-08 | 3 | 2021 | September | North | 51141-8338_MW_EXP_NEW_K | ATP | xad_hasnian | 4 | 1 | Utilized | No Show |  | Pending |  |  | Rain
2021-09-08 | 3 | 2021 | September | North | 50831-POWER-EXP-I | QC | xad_saqib | 3 |  | Utilized | No Show |  | Completed | Closed
2021-09-08 | 3 | 2021 | September | North | RUR2596_RRU-MOD_NEW_P | I&C | xad_akbar1 | 1 |  | Utilized | late | Closed | Pending |  |  | Rain
2021-09-08 | 3 | 2021 | September | North | 51203-GL900-Exp-P | Survey | xad_atif | 1 |  | Utilized | late | Closed | Completed
2021-09-08 | 3 | 2021 | September | North | 8024-POWER-EXP-P | Survey | xad_shahzad1 | 1 |  | Utilized | late | Closed | Completed
2021-09-08 | 3 | 2021 | September | North | DHD1290_RRU-MOD_NEW_P | I&C | xad_ghazenfar | 1 |  | Utilized | late | Closed | Pending
2021-09-08 | 3 | 2021 | September | North | 51201-GL900-Exp-P | Survey | xad_imran | 2 | 1 | Utilized | late | Closed | Completed
2021-09-08 | 3 | 2021 | September | North | 52188-GL900-Exp-P | Survey | xad_baseer | 3 | 2 | Utilized | late | Closed | Pending
2021-09-09 | 3 | 2021 | September | North | 50969-POWER-EXP-I | Power I&C | xad_saqib | 2 |  | Utilized | On Time | Closed | Completed | Closed
2021-09-09 | 3 | 2021 | September | North | RWP5171_2G-L900-LTE_NEW_P | ATP | xad_atif1 | 6 | 3 | Utilized | No Show |  | Pending
2021-09-09 | 3 | 2021 | September | North | 3197-9010_MW_SWAP_NEW_K | MW I&C | xad_hasnian | 1 |  | Utilized | Late | Closed | In progress
2021-09-09 | 3 | 2021 | September | North | RUR2596_RRU-MOD_NEW_P | I&C | xad_akbar1 | 2 |  | Utilized | On Time | Closed | In progress
2021-09-09 | 3 | 2021 | September | North | 51212-GL900-Exp-P | Survey | xad_atif | 4 | 3 | Utilized | On Time | Closed | Completed
2021-09-09 | 3 | 2021 | September | North | 51747-GL900-Exp-P | Survey | xad_atif | 3 | 2 | Utilized | On Time | Closed | Pending
2021-09-09 | 3 | 2021 | September | North | 3165-POWER-EXP-K | Survey | xad_shahzad1 | 3 | 2 | Utilized | Late | Rejected/Closed | Completed
2021-09-09 | 3 | 2021 | September | North | DHD1290_RRU-MOD_NEW_P | I&C | xad_ghazenfar | 2 |  | Utilized | On Time | Closed | In progress
2021-09-09 | 3 | 2021 | September | North | 51619-GL900-Exp-P | Survey | xad_imran | 1 |  | Utilized | Late | Closed | Completed
2021-09-09 | 3 | 2021 | September | North | 51141-8338_MW_EXP_NEW_K | ATP | xad_waseem | 5 | 2 | Utilized | No Show |  | Pending | Closed
2021-09-10 | 3 | 2021 | September | North | 9290-POWER-NOMC-I | Pre ATP | xad_saqib | 1 |  | Utilized
2021-09-10 | 3 | 2021 | September | North | RWP5171_2G-L900-LTE_NEW_P | ATP | xad_atif1 | 7 | 4 | Utilized |  |  |  | Closed
2021-09-10 | 3 | 2021 | September | North | 3197-9010_MW_SWAP_NEW_K | MW I&C | xad_hasnian | 2 |  | Utilized | On Time | Closed
2021-09-10 | 3 | 2021 | September | North | RUR2596_RRU-MOD_NEW_P | I&C | xad_akbar1 | 3 |  | Utilized | On Time | Closed |  | Closed
2021-09-10 | 3 | 2021 | September | North | 51747-GL900-Exp-P | Survey | xad_atif | 4 | 3 | Utilized | On Time | Closed
2021-09-10 | 3 | 2021 | September | North | 50806-POWER-EXP-I | Survey | xad_shahzad1 | 1 |  | Utilized | Late | Closed
2021-09-10 | 3 | 2021 | September | North | DHD1290_RRU-MOD_NEW_P | I&C | xad_ghazenfar | 3 |  | Utilized | On Time | Closed
2021-09-10 | 3 | 2021 | September | North | 51286-GL900-Exp-P | Survey | xad_imran | 1 |  | Utilized | On Time | Closed
2021-09-10 | 3 | 2021 | September | North | 52719-GL900-Exp-I | ATP | xad_waseem | 3 |  | Utilized
2021-09-11 | 3 | 2021 | September | North | TLG2779_4T6S_NEW_P | I&C | xad_akbar1 | 1 |  | Utilized | Late | Closed
2021-09-11 | 3 | 2021 | September | North | 50795-GL900-Exp-P | Pre ATP | xad_atif1 | 6 | 3 | Utilized | No Show
2021-09-11 | 3 | 2021 | September | North | 3197-9010_MW_SWAP_NEW_K | MW I&C | xad_hasnian | 3 |  | Utilized | On Time | R/Closed |  | Closed
2021-09-11 | 3 | 2021 | September | North | UFMGY3 Opex_2687_PWR_Swap_K | Troubleshooting | xad_saqib | 2 |  | Utilized | Late | Closed |  | Closed
2021-09-11 | 3 | 2021 | September | North | 51747-GL900-Exp-P | Survey | xad_atif | 5 | 4 | Utilized | On Time | R/Closed
2021-09-11 | 3 | 2021 | September | North | 9593-POWER-EXP-P | Survey | xad_shahzad1 | 1 |  | Utilized | Late | Closed
2021-09-11 | 3 | 2021 | September | North | DHD1290_RRU-MOD_NEW_P | I&C | xad_ghazenfar | 4 | 1 | Utilized | Late | Closed |  | Closed
2021-09-11 | 3 | 2021 | September | North | 51286-GL900-Exp-P | Survey | xad_imran | 2 | 1 | Utilized | Late | Closed
2021-09-11 | 3 | 2021 | September | North | 9290-POWER-NOMC-I | Pre ATP | xad_waseem | 2 |  | Utilized | No Show
2021-09-12 | 3 | 2021 | September | North | TLG2779_4T6S_NEW_P | I&C | xad_akbar1 | 2 |  | Utilized | On Time
2021-09-12 | 3 | 2021 | September | North | RUR4690_LTE_NEW_K | I&C | xad_adeel | 1 |  | Utilized | No Show
2021-09-12 | 3 | 2021 | September | North | 50758-POWER-EXP-P | Pre ATP | xad_hasnian | 2 |  | Utilized | Late | Closed
2021-09-12 | 3 | 2021 | September | North | KSD1562_RUR3217_Link_2_K | MW I&C | xad_saqib | 1 |  | Utilized | No Show
2021-09-12 | 3 | 2021 | September | North | 51285-GL900-Exp-P | Survey | xad_atif | 1 |  | Utilized | On Time | Closed
2021-09-12 | 3 | 2021 | September | North | 3219-POWER-EXP-P | Survey | xad_shahzad1 | 1 |  | Utilized | Late | Closed
2021-09-12 | 3 | 2021 | September | North | RUR4339_LTE_NEW_F | I&C | xad_ghazenfar | 1 |  | Utilized | No Show
2021-09-12 | 3 | 2021 | September | North | 51022-GL900-Exp-P | Survey | xad_imran | 1 |  | Utilized | On Time | Closed
2021-09-12 | 3 | 2021 | September | North | 50809-POWER-EXP-P | Pre ATP | xad_waseem | 1 |  | Utilized | No Show
2021-09-12 | 3 | 2021 | September | North | RUR4376_LTE_NEW_F | I&C | xad_baseer | 1 |  | Utilized | No Show
2021-09-13 | 3 | 2021 | September | North | TLG2779_4T6S_NEW_P | I&C | xad_akbar1 | 3 |  | Utilized | On Time | Closed
2021-09-13 | 3 | 2021 | September | North | RWP5171_RWP1213_Link_1_P | Pre ATP | xad_adeel | 3 |  | Utilized | No Show |  |  | Closed
2021-09-13 | 3 | 2021 | September | North | 50795-GL900-Exp-P | Pre ATP | xad_hasnian | 7 | 4 | Utilized | Late | Closed
2021-09-13 | 3 | 2021 | September | North | KSD1562_RUR3217_Link_2_K | MW I&C | xad_saqib | 2 |  | Utilized | On Time | Closed
2021-09-13 | 3 | 2021 | September | North | 9456-GL900-Exp-P | Survey | xad_atif | 1 |  | Utilized | On Time | Closed
2021-09-13 | 3 | 2021 | September | North | 9593-POWER-EXP-P | Survey | xad_shahzad1 | 2 | 1 | Utilized | No Show
2021-09-13 | 3 | 2021 | September | North | RUR4339_LTE_NEW_F | I&C | xad_ghazenfar | 2 |  | Utilized | On Time | Closed |  | Closed
2021-09-13 | 3 | 2021 | September | North | 52407-GL900-Exp-I | Survey | xad_atif1 | 1 |  | Utilized | No Show
2021-09-13 | 3 | 2021 | September | North | 50809-POWER-EXP-P | Pre ATP | xad_waseem | 2 |  | Utilized | No Show
2021-09-13 | 3 | 2021 | September | North | RUR4376_LTE_NEW_F | I&C | xad_baseer | 2 |  | Utilized | No Show
[5 empty] | 3025-POWER-EXP-P | Survey | xad_shahzad1 | 1 |  | Utilized | On Time | Closed

## Sheet1
total activiates | which one
total teamas
repeat activaties
resource/teams
comparasion | revenuew |  | cost | p/l %
D | Project Code | Site Code | Sub Contract NO. | PR NO. | PO Status | PO NO. | PO Line NO. | Item Code | Item Description | Requested Qty | Due Qty | Unit Price | Line Amount | Unit | Tax Rate | Currency | Payment Terms | Payment Method | Bill To | Ship To | Engineering Code | Engineering Name | Subproject Code | Category | Center Area | Product Category | Start Date | End Date | Expire Date | Publish Date | Acceptance Date | Note to Receiver | Fob Lookup Code | Acceptance Date
130276319501 | 56A0E94 | 97-GCSS CORE-OSN9800-EXP-S | FPA1021PAK20121610070105/-B1 | 10210225707 | NEW | 102121379447-340 | 1 | 88122EJJ | Optical Network,Hardware Installation for Expansion,Per 1 to 8 Ports | 2 | 2 | 2240 | 4480 | PCS | 16% | PKR | 【TT】▍AC1 (70%, INV AC -30D, Complete 70%) / AC2 (30%, INV AC -30D, Complete 100%) ▍ | TT | Ali Akbar 00315229,Finance Department,12th, Saudi Pak Tower, Blue Area, Islamabad,PK,0092-51-280000-210,0092-51-2800015 | Huawei Technologies Co., PK. Ltd,12th,Saudi Pak Tower, Blue Area, Islamabad,PK |  |  | 499JYRX | ENGINEERING_SERVICE.TELECOM_EQUIPMENT_ENGINEERING.HARDWARE_INSTALLATION |  |  | 2021-09-22 | 2021-12-31 |  | 2021-09-15 18:00 |  |  | REFER TO AGREEMENT
130276319701 | 56A0E94 | 97-GCSS CORE-OSN9800-EXP-S | FPA1021PAK20121610070105/-B1 | 10210225707 | NEW | 102121379447-340 | 2 | 88121MFH | Site visit,Per Site | 1 | 1 | 4095 | 4095 | PCS | 16% | PKR | 【TT】▍AC1 (70%, INV AC -30D, Complete 70%) / AC2 (30%, INV AC -30D, Complete 100%) ▍ | TT | Ali Akbar 00315229,Finance Department,12th, Saudi Pak Tower, Blue Area, Islamabad,PK,0092-51-280000-210,0092-51-2800015 | Huawei Technologies Co., PK. Ltd,12th,Saudi Pak Tower, Blue Area, Islamabad,PK |  |  | 499JYRX | ENGINEERING_SERVICE.TELECOM_EQUIPMENT_ENGINEERING.HARDWARE_INSTALLATION |  |  | 2021-09-22 | 2021-12-31 |  | 2021-09-15 18:00 |  |  | REFER TO AGREEMENT
130342293501 | 56A0E94 | 97-GCSS-PTN7900-EXP-S | FPA1021PAK20121610070105/-B1 | 10210225842 | NEW | 102121379447-355 | 1 | 8812252618 | Module level transportation new level 3 Forward -/TRP | 1 | 1 | 7400 | 7400 | SITE | 16% | PKR | 【TT】▍AC1 (100%, INV AC -30D, Complete 100%) ▍ | TT | Ali Akbar 00315229,Finance Department,12th, Saudi Pak Tower, Blue Area, Islamabad,PK,0092-51-280000-210,0092-51-2800015 | Huawei Technologies Co., PK. Ltd,12th,Saudi Pak Tower, Blue Area, Islamabad,PK |  |  | 499JYRX | ENGINEERING_SERVICE.TELECOM_EQUIPMENT_ENGINEERING.Engineering_Logistics |  |  | 2021-09-23 | 2021-12-31 |  | 2021-09-16 16:36 |  |  | REFER TO AGREEMENT
130342294001 | 56A0E94 | 97-GCSS-PTN7900-EXP-S | FPA1021PAK20121610070105/-B1

## Center
[5 empty] | 112 |  | 110 |  | 2021-09-21
Date | Quarter | Year | Month | Region | DU ID | Scope | Team Lead | Total Planned days | SLA Breach aging | Team Status | Clock in Status | EHS Status | Activity Status | Q/C Status | ATP Status
2021-08-25 | 3 | 2021 | August | Center | LHR5872_L2100_NEW_P | Wireless I&C | Xad_Saifullah | 1 |  | Utilized | No Show |  | Pending | In review
2021-08-25 | 3 | 2021 | August | Center | LHR5872_L2100_NEW_P | Microwave I&C | xad_sharjeel | 2 |  | Utilized | late | Closed | In progress | In review
2021-08-25 | 3 | 2021 | August | Center | SKT1620_L2100_NEW_P | Wireless I&C | xad_arslanhaider | 1 |  | Utilized | late | Closed | In progress | In review
2021-08-25 | 3 | 2021 | August | Center | 43448-POWER-NEW-P | Power I&C | xad_sohail | 1 |  | Utilized | On Time | Closed | Completed | Closed
2021-08-25 | 3 | 2021 | August |  | 43448-3G-4G-NEW-P | Wireless I&C |  | 1 |  | Utilized | On Time | Closed | Completed | Closed
2021-08-25 | 3 | 2021 | August | Center | RUR1051_RRU-MOD_NEW_P | ATP | xad_aliraza | 1 |  | Utilized | late | Closed | Completed | Not applicable | Done
2021-08-26 | 3 | 2021 | August | Center | 43352-7252_MW_RO_NEW_P | Microwave I&C | Xad_Saifullah | 1 |  | Utilized | On Time | Closed |  | Closed
2021-08-26 | 3 | 2021 | August | Center | LHR5872_L2100_NEW_P | Wireless I&C | xad_sharjeel | 3 |  | Utilized | Late | Closed |  | Rejected
2021-08-26 | 3 | 2021 | August | Center | SKT1620_L2100_NEW_P | Wireless I&C | xad_arslanhaider | 2 |  | Utilized | On Time | Closed |  | Closed
2021-08-26 | 3 | 2021 | August | Center | 6133-POWER-NOMC-P | ATP | xad_sohail | 1 |  | Utilized | No show |  |  | Not applicable
2021-08-26 | 3 | 2021 | August | Center | AHM8025_RRU-MOD_NEW_P | ATP | xad_aliraza | 1 |  | Utilized | Late | Closed |  | Not applicable
2021-08-27 | 3 | 2021 | August | Center | 43352-7252_MW_RO_NEW_P | Microwave I&C | Xad_Saifullah | 2 |  | Utilized | Late | Closed | Completed | In review
2021-08-27 | 3 | 2021 | August | Center | LHR5829_L2100_NEW_P | Wireless I&C | xad_sharjeel | 1 |  | Utilized | Late | Closed | In progress | In review
2021-08-27 | 3 | 2021 | August | Center | SKT5523_L2100_NEW_P | Wireless I&C | xad_arslanhaider | 1 |  | Utilized | On Time | Closed | In progress
2021-08-27 | 3 | 2021 | August | Center | 7098-4212_MW_MOD_NEW_P | Microwave I&C | xad_sohail | 1 |  | Utilized | Late | Closed | Completed | In review
2021-08-27 | 3 | 2021 | August | Center | RUR1127_RRU-MOD_NEW_P | ATP | xad_aliraza | 1 |  | Utilized | No show |  | Pending | Not applicable
2021-08-28 | 3 | 2021 | August | Center | LHR5654_L2100_NEW_P | Wireless I&C | Xad_Saifullah | 1 |  | Utilized |  |  | In progress
2021-08-28 | 3 | 2021 | August | Center | LHR5695_L2100_NEW_P | Wireless I&C | xad_sharjeel | 1 |  | Utilized |  |  | Completed
2021-08-28 | 3 | 2021 | August | Center | SKT5523_L2100_NEW_P | Wireless I&C | xad_arslanhaider | 2 |  | Utilized |  |  | Completed | Closed
2021-08-28 | 3 | 2021 | August | Center | 5268-5300_MW_SDB_NEW_P | Microwave I&C | xad_sohail | 1 |  | Utilized |  |  | In progress
2021-08-28 | 3 | 2021 | August | Center | 43312-5268_MW_NPS_NEW_P | Microwave I&C | xad_waqar1 | 1 |  | Utilized |  |  | In progress
2021-08-28 | 3 | 2021 | August | Center | LHR5829_L2100_NEW_P | Wireless I&C | xad_aliraza | 2 |  | Utilized |  |  | Completed
2021-08-29 | 3 | 2021 | August | Center | LHR5654_L2100_NEW_P | Wireless I&C | Xad_Saifullah | 2 |  | Utilized | On Time | Closed | Completed
2021-08-29 | 3 | 2021 | August | Center | KMK9799_RRU-MOD_NEW_P | Wireless I&C | xad_sharjeel | 1 |  | Utilized | Late | Closed | In Progress
2021-08-29 | 3 | 2021 | August | Center | GMW9713_RRU-MOD_NEW_P | Wireless I&C | xad_arslanhaider | 1 |  | Utilized | Late | Closed | In Progress
2021-08-29 | 3 | 2021 | August | Center | 5268-5300_MW_SDB_NEW_P | Microwave I&C | xad_sohail | 2 |  | Utilized | On Time | Closed | Completed
2021-08-29 | 3 | 2021 | August | Center | LHR5695_L2100_NEW_P | Wireless I&C | xad_aliraza | 2 |  | Utilized | On Time | Closed | Completed
2021-08-29 | 3 | 2021 | August | Center | 43312-5268_MW_NPS_NEW_P | Microwave I&C | xad_waqar1 | 2 |  | Utilized | On Time | Closed | In Progress
2021-08-30 | 3 | 2021 | August | Center | HWY7487_RRU-MOD_NEW_P | Wireless I&C | Xad_Saifullah | 1 |  | Utilized | Late | closed | In Progress
2021-08-30 | 3 | 2021 | August | Center | KMK9799_RRU-MOD_NEW_P | Wireless I&C | xad_sharjeel | 2 |  | Utilized | Late | closed | Completed
2021-08-30 | 3 | 2021 | August | Center | GMW9713_RRU-MOD_NEW_P | Wireless I&C | xad_arslanhaider | 2 |  | Utilized | Late | closed | Completed
2021-08-30 | 3 | 2021 | August | Center | 6564-7008_MW_XPIC_NEW_P | ATP | xad_sohail | 1 |  | Utilized | No Show |  | Completed |  | Done
2021-08-30 | 3 | 2021 | August | Center | SKT1620_L2100_NEW_P | ATP | xad_aliraza | 3 |  | Utilized | Late | closed | Completed |  | Done
2021-08-30 | 3 | 2021 | August | Center | 43312-5268_MW_NPS_NEW_P | Microwave I&C | xad_waqar1 | 3 |  | Utilized | Late | Rejected/Closed | Completed
2021-08-31 | 3 | 2021 | August | Center | HWY7487_RRU-MOD_NEW_P | Wireless I&C | Xad_Saifullah | 2 |  | Utilized | On Time | Closed | In progress
2021-08-31 | 3 | 2021 | August | Center | SHK6932_RRU-MOD_NEW_P | Wireless I&C | xad_sharjeel | 1 |  | Utilized | No Show |  | In progress
2021-08-31 | 3 | 2021 | August | Center | HWY8870_RRU-MOD_NEW_P | Wireless I&C | xad_arslanhaider | 1 |  | Utilized | Late | Closed | In progress
2021-08-31 | 3 | 2021 | August | Center | 5268-5300_MW_SDB_NEW_P | ATP | xad_sohail | 3 |  | Utilized | Late | Closed | Pending
2021-08-31 | 3 | 2021 | August | Center | LHR5654_L2100_NEW_P | ATP | xad_aliraza | 3 |  | Utilized | No Show |  | Pending
2021-08-31 | 3 | 2021 | August | Center | LHR5695_L2100_NEW_P | ATP | xad_aliraza | 3 |  | Utilized | No Show |  | Pending | Closed
2021-08-31 | 3 | 2021 | August | Center | 43312-3G-4G-NEW-P | Wireless I&C | xad_waqar1 | 1 |  | Utilized | Late | Closed | In progress | Closed
2021-09-01 | 3 | 2021 | September | Center | HWY7487_RRU-MOD_NEW_P | Wireless I&C | Xad_Saifullah | 3 |  | Utilized | On Time | Closed | Completed | Closed | Done
2021-09-01 | 3 | 2021 | September | Center | SHK6932_RRU-MOD_NEW_P | Wireless I&C | xad_sharjeel | 2 |  | Utilized | On Time | Closed | In progress
2021-09-01 | 3 | 2021 | September | Center | HWY8870_RRU-MOD_NEW_P | Wireless I&C | xad_arslanhaider | 2 |  | Utilized | On Time | Rejected/Closed | Completed
2021-09-01 | 3 | 2021 | September | Center | 6415-5268_MW_MIMO_NEW_P | ATP | xad_sohail | 1 |  | Utilized | On Time | Closed | Completed |  | Done
2021-09-01 | 3 | 2021 | September | Center | GMW9713_RRU-MOD_NEW_P | ATP | xad_aliraza | 3 |  | Utilized | On Time | Closed | Pending
2021-09-01 | 3 | 2021 | September | Center | 43312-3G-4G-NEW-P | ATP | xad_waqar1 | 2 |  | Utilized | No Show |  | Pending
2021-09-02 | 3 | 2021 | September | Center | 4885-POWER-NOMC-P | Power I&C | Xad_Saifullah | 1 |  | Utilized | On Time | Closed | In progress
2021-09-02 | 3 | 2021 | September | Center | SHK6932_RRU-MOD_NEW_P | Wireless I&C | xad_sharjeel | 3 |  | Utilized | On Time | Closed | Completed
2021-09-02 | 3 | 2021 | September | Center | PTT3073_RRU-MOD_NEW_P | Wireless I&C | xad_arslanhaider | 1 |  | Utilized | On Time | Closed | In progress
2021-09-02 | 3 | 2021 | September | Center | HWY8870_RRU-MOD_NEW_P | Troubleshooting |  | 3 |  | Utilized | No Show |  | Completed
2021-09-02 | 3 | 2021 | September | Center | 43448-4155_MW_NPS_NEW_P | ATP | xad_sohail | 1 |  | Utilized | No Show |  | Completed |  | Done
2021-09-02 | 3 | 2021 | September | Center | GJR6908_4T6S_NEW_P | ATP | xad_aliraza | 1 |  | Utilized | No Show |  | Completed |  | Done
2021-09-02 | 3 | 2021 | September | Center | 43312-5268_MW_NPS_NEW_P | ATP | xad_waqar1 | 4 | 1 | Utilized | Late | Closed | Pending | Closed
2021-09-03 | 3 | 2021 | September | Center | 4885-POWER-NOMC-P | Power I&C | Xad_Saifullah | 2 |  | Utilized | On Time | Closed | Completed
2021-09-03 | 3 | 2021 | September | Center | 43352-7252_MW_RO_NEW_P | ATP | xad_sharjeel | 3 |  | Utilized | No Show |  | Pending
2021-09-03 | 3 | 2021 | September | Center | PTT3073_RRU-MOD_NEW_P | Wireless I&C | xad_arslanhaider | 2 |  | Utilized | On Time | Closed | In progress
2021-09-03 | 3 | 2021 | September | Center | 6225-6415_MW_XPIC_NEW_P | Microwave I&C | xad_sohail | 1 |  | Utilized | Late | Closed | In progress
2021-09-03 | 3 | 2021 | September | Center | LHR5654_L2100_NEW_P | ATP | xad_aliraza | 4 | 1 | Utilized | No Show |  | Completed | Closed | Done
2021-09-03 | 3 | 2021 | September | Center | 43011-3G-4G-NEW-P | ATP | xad_waqar1 | 1 |  | Utilized | No Show |  | Pending
2021-09-03 | 3 | 2021 | September | Center | 40888-POWER-EXP-P | Survey | xad_Ahmed | 1 |  | Utilized | late | Closed | Pending
2021-09-03 | 3 | 2021 | September | Center | 40749-POWER-EXP-P | Survey | xad_Ahmed | 1 |  | Utilized | No Show |  | Pending
2021-09-04 | 3 | 2021 | September | Center | HWY8819_RRU-MOD_NEW_P | Wireless I&C | xad_sharjeel | 1 |  | Utilized
2021-09-04 | 3 | 2021 | September | Center | PTT3073_RRU-MOD_NEW_P | Wireless I&C | xad_arslanhaider | 3 |  | Utilized |  |  |  | Closed
2021-09-04 | 3 | 2021 | September | Center | 6225-6415_MW_XPIC_NEW_P | Microwave I&C | xad_sohail | 2 |  | Utilized
2021-09-04 | 3 | 2021 | September | Center | 40749-POWER-EXP-P | Survey | xad_waqar1 | 2 | 1 | Utilized
2021-09-05 | 3 | 2021 | September | Center | HWY8819_RRU-MOD_NEW_P | Wireless I&C | xad_sharjeel | 2 |  | Utilized
2021-09-05 | 3 | 2021 | September | Center | WZB9803_RRU-MOD_NEW_P | Wireless I&C | xad_arslanhaider | 1 |  | Utilized
2021-09-05 | 3 | 2021 | September | Center | 4747-5214_MW_XPIC_NEW_P | Microwave I&C | xad_saifullah | 1 |  | Utilized
2021-09-05 | 3 | 2021 | September | Center | 6225-6415_MW_XPIC_NEW_P | Microwave I&C | xad_sohail | 3 |  | Utilized |  |  |  | Closed
2021-09-05 | 3 | 2021 | September | Center | 40888-POWER-EXP-P | ATP | xad_waqar1 | 2 |  | Utilized
2021-09-06 | 3 | 2021 | September | Center | HWY8819_RRU-MOD_NEW_P | Wireless I&C | xad_sharjeel | 3 |  | Utilized | On Time | Closed | Completed | Closed
2021-09-06 | 3 | 2021 | September | Center | WZB9803_RRU-MOD_NEW_P | Wireless I&C | xad_arslanhaider | 2 |  | Utilized | On Time | Closed | In progress
2021-09-06 | 3 | 2021 | September | Center | 4747-5214_MW_XPIC_NEW_P | Microwave I&C | xad_saifullah | 2 |  | Utilized | On Time | Closed | Completed | Closed
2021-09-06 | 3 | 2021 | September | Center | 5268-5300_MW_SDB_NEW_P | ATP | xad_sohail | 4 | 1 | Utilized | No Show |  | Completed |  | Done
2021-09-06 | 3 | 2021 | September | Center | MegaPO3_5650-4288_RTN_Dismantling_P | Microwave Dismantling | xad_sohail | 1 |  | Utilized | Late | Closed | Pending
2021-09-06 | 3 | 2021 | September | Center | 42563-POWER-EXP_P | Survey | xad_waqar1 | 1 |  | Utilized | Late | Closed | Completed
2021-09-06 | 3 | 2021 | September | Center | HWY8870_RRU-MOD_NEW_P | ATP | xad_aliraza | 4 | 1 | Utilized | No Show |  | Pending | Closed
2021-09-07 | 3 | 2021 | September | Center | RUR0217_RRU-MOD_NEW_P | Wireless I&C | xad_sharjeel | 1 |  | Utilized | No show |  | In progress
2021-09-07 | 3 | 2021 | September | Center | WZB9803_RRU-MOD_NEW_P | Wireless I&C | xad_arslanhaider | 3 |  | Utilized | On Time | Closed | In progress | Closed
2021-09-07 | 3 | 2021 | September | Center | 6520-4747_MW_XPIC_NEW_P | Microwave I&C | xad_saifullah | 1 |  | Utilized | On Time | Closed | In progress
2021-09-07 | 3 | 2021 | September | Center | 43352-7252_MW_RO_NEW_P | ATP | xad_waqar1 | 4 | 1 | Utilized | No show |  | Pending
2021-09-07 | 3 | 2021 | September | Center | MegaPO3_5650-4288_RTN_Dismantling_P | Microwave Dismantling | xad_sohail | 2 |  | Utilized | No show |  | Pending
2021-09-07 | 3 | 2021 | September | Center | 42394-POWER-EXP_P | Survey | xad_waqar1 | 1 |  | Utilized | Late | Closed | In progress
2021-09-07 | 3 | 2021 | September | Center | SHK6932_RRU-MOD_NEW_P | ATP | xad_aliraza | 4 | 1 | Utilized | Late | Closed | Completed | Closed | Done
2021-09-08 | 3 | 2021 | September | Center | RUR0217_RRU-MOD_NEW_P | Wireless I&C | xad_sharjeel | 2 |  | Utilized | On Time | Closed | In progress
2021-09-08 | 3 | 2021 | September | Center | LHR1421_RRU-MOD_NEW_P | Wireless I&C | xad_arslanhaider | 1 |  | Utilized | late | Closed | Pending
2021-09-08 | 3 | 2021 | September | Center | 6520-4747_MW_XPIC_NEW_P | Microwave I&C | xad_saifullah | 2 |  | Utilized | On Time | Closed | Completed | Closed
2021-09-08 | 3 | 2021 | September | Center | 4885-POWER-NOMC-P | ATP | xad_sharjeel | 3 |  | Utilized | No Show |  | Completed | Closed | Done
2021-09-08 | 3 | 2021 | September | Center | MegaPO3_5650-4288_RTN_Dismantling_P | Microwave Dismantling | xad_sohail | 3 |  | Utilized | On Time | Closed | Completed | Closed
2021-09-08 | 3 | 2021 | September | Center | 40749-POWER-EXP_P | Survey | xad_waqar1 | 1 |  | Utilized | late | Closed | Completed
2021-09-08 | 3 | 2021 | September | Center | 40888-POWER-EXP-P | Survey | xad_waqar1 | 3 | 2 | Utilized | No Show |  | Pending
2021-09-08 | 3 | 2021 | September | Center | GMW9713_RRU-MOD_NEW_P | ATP | xad_aliraza | 1 |  | Utilized | On Time | Closed | Pending
2021-09-08 | 3 | 2021 | September | Center | RUR0763_RRU-MOD_NEW_P | Wireless I&C | Xad_arslanhaider | 1 |  | Utilized | late | Closed | In progress
2021-09-09 | 3 | 2021 | September | Center | RUR0217_RRU-MOD_NEW_P | Wireless I&C | xad_sharjeel | 3 |  | Utilized | On Time | Rejected/Closed | In progress
2021-09-09 | 3 | 2021 | September | Center | RUR0763_RRU-MOD_NEW_P | Wireless I&C | xad_arslanhaider | 2 |  | Utilized | On Time | Closed | In progress
2021-09-09 | 3 | 2021 | September | Center | 4522-5829_MW_XPIC_NEW_P | Microwave I&C | xad_saifullah | 1 |  | Leave | No Show |  | Pending
2021-09-09 | 3 | 2021 | September | Center | MegaPO3_5675-5672_RTN_HUG_P | Microwave I&C | xad_sohail | 1 |  | Utilized | Late | Closed | Pending
2021-09-09 | 3 | 2021 | September | Center | 42620-POWER-EXP_P | Survey | xad_waqar1 | 1 |  | Utilized | Late | Closed | Completed
2021-09-09 | 3 | 2021 | September | Center | KMK9799_RRU-MOD_NEW_P | ATP | xad_aliraza | 3 |  | Utilized | No Show |  | Completed | Closed | Done
2021-09-09 | 3 | 2021 | September | Center | RUR1051_RRU-MOD_NEW_P | ATP | xad_aliraza | 2 |  | Utilized | No Show |  | Completed |  | Done
2021-09-10 | 3 | 2021 | October | Center | RUR0217_RRU-MOD_NEW_P | Wireless I&C | xad_sharjeel | 4 | 1 | Utilized | On Time | Closed |  | Closed
2021-09-10 | 3 | 2021 | November | Center | RUR0763_RRU-MOD_NEW_P | Wireless I&C | xad_arslanhaider | 3 |  | Utilized | On Time | Rejected/Closed |  | Closed
2021-09-10 | 3 | 2021 | December | Center | 4522-5829_MW_XPIC_NEW_P | Microwave I&C | xad_saifullah | 2 |  | Utilized | On Time | Closed |  | Closed
2021-09-10 | 3 | 2021 | January | Center | MegaPO3_CII-2071-5580_RTN_RR_P | Microwave I&C | xad_sohail | 1 |  | Utilized | Late | Closed |  | Rejected
2021-09-10 | 3 | 2021 | February | Center | 40749-POWER-EXP-P | Survey | xad_waqar1 | 3 | 2 | Utilized
2021-09-10 | 3 | 2021 | March | Center | 40888-POWER-EXP-P | Survey | xad_ahmed | 4 | 3 | Utilized | On Time | Closed
2021-09-10 | 3 | 2021 | April | Center | LHR5695_L2100_NEW_P | ATP | xad_aliraza | 4 | 1 | Utilized
2021-08-29 | 3 | 2021 | August | Center | GMW9713_RRU-MOD_NEW_P | Wireless I&C | xad_arslanhaider | 1 |  | Utilized | Late | Closed | In Progress
2021-08-30 | 3 | 2021 | August | Center | GMW9713_RRU-MOD_NEW_P | Wireless I&C | xad_arslanhaider | 2 |  | Utilized | Late | closed | Completed | Closed
2021-09-01 | 3 | 2021 | September | Center | GMW9713_RRU-MOD_NEW_P | ATP | xad_aliraza | 3 |  | Utilized | On Time | Closed | Pending
2021-09-08 | 3 | 2021 | September | Center | GMW9713_RRU-MOD_NEW_P | ATP | xad_aliraza | 1 |  | Utilized | On Time | Closed | Pending